## KPI System
Project Name | Client Name | Role | Team Member Name | Task Description | Assigned Date | Due Date | Actual Completion Date | On-Time? | Revisions / Errors | QC Passed? | Material Used? | Waste Quantity | Cost per Unit (₱) | Reason for Waste | Client Feedback (PM Only) | Notes / Issues | Task Type | Output % | Timeliness % | Accuracy % | Teamwork % | Error/Revision Category | Client Satisfaction Score (CSAT) | Planned Material Quantity | Material Efficiency % | Overall KPI % | Color Code
Project A | Teviant | Designer | Dimple Vergara | 3D Layout | 2025-06-01 | 2025-06-03 | 2025-06-03 | Yes | 1 | Yes | No |  |  |  |  | Minor alignment tweak needed | Individual | 100 | 100 | 90 | 95 | Design Issue |  |  |  | 95.75 | Green
Project A | Teviant | Project Manager | Jacky Eñaga | Client Communication | 2025-06-01 | 2025-06-03 | 2025-06-03 | Yes | 0 | Yes | No |  |  |  | 9 | No issues | Individual | 85 | 95 | 100 | 100 |  |  |  |  | 95.5 | Green
Project A | Teviant | Designer | Dimple Vergara | Technical Drawing | 2025-06-01 | 2025-06-03 | 2025-06-03 | Yes | 0 | Yes | No |  |  |  |  | No issues | Individual | 77 | 80 | 90 | 80 |  |  |  |  | 82.75 | Yellow
Project A | Teviant | Project Manager | Jacky Eñaga | Client proposal | 2025-06-02 | 2025-06-07 | 2025-06-08 | No | 1 | Yes | No |  |  |  | organize better | late submission | Individual | 90 | 70 | 85 | 80 |  |  |  |  | 80 | Yellow
Project B | GRWM | Fabricator | Ryan Dela Cruz | Cutting & Assembling | 2025-06-02 | 2025-06-07 | 2025-06-07 | Yes | 0 | Yes | Yes | 0.25 | 1100 | cut due to spacing |  | No issues | Team | 90 | 90 | 99 | 100 |  |  |  | #VALUE!

## Role-Specific Weights
Role | Output Weight | Timeliness Weight | Accuracy Weight | Teamwork Weight | Material Efficiency Weight | Total Weight
Designer | 0.25 | 0.25 | 0.35 | 0.15 | 0 | 1
Project Manager | 0.2 | 0.3 | 0.2 | 0.3 | 0 | 1
Estimator | 0.2 | 0.3 | 0.4 | 0.1 | 0 | 1
Fabricator | 0.25 | 0.2 | 0.2 | 0.2 | 0.15 | 1
CNC Operator | 0.25 | 0.2 | 0.3 | 0.1 | 0.15 | 1
Painter | 0.3 | 0.2 | 0.35 | 0.15 | 0 | 1
Electrician | 0.1 | 0.3 | 0.4 | 0.2 | 0 | 1
Project Coordinator / Admin | 0.3 | 0.35 | 0.2 | 0.15 | 0 | 1
Accounting | 0.1 | 0.4 | 0.4 | 0.1 | 0 | 1

## Legend
Column | Description
Project Name | Name of the project
Client Name | Client’s company or brand
Role | Role of the person being scored
Team Member Name | Full name of the staff member
Task Description | Brief description of task
Assigned Date | When task was assigned
Due Date | When the task was due
Actual Completion Date | Actual date the task was completed
On-Time? | Yes/No if the task was on time
Revisions / Errors | Count of revisions/errors
QC Passed? | Did the task pass quality check?
Material Used? | Was any material used?
Waste Quantity | Amount of material wasted
Cost per Unit (₱) | Unit cost of wasted material
Reason for Waste | Why the waste happened
Client Feedback (PM Only) | Only for PMs – feedback score from client
Notes / Issues | Other blockers or details
Task Type | 'Individual' or 'Team'
Output % | Score based on volume of work done
Timeliness % | Score based on punctuality
Accuracy % | Score based on quality
Teamwork % | Score based on communication
Overall KPI % | Auto-calculated weighted score
Color Code | Auto-assigned based on score

## Scoring Guide
Score Range | Performance Level | Output | Timeliness | Accuracy | Teamwork
90–100% | Excellent | Exceeded expectations, supported others | Always early or on-time | Flawless or 1 minor revision | Consistent updates, helped coordination
80–89% | Good | Completed most tasks effectively | 1 minor delay | 2–3 errors, not critical | Usually responsive, small gaps
70–79% | Needs Improvement | Multiple tasks incomplete or delayed | More than 1 delay | Significant issues or backjobs | Often unresponsive, unclear handoffs
<70% | Poor | Failed key deliverables | Frequent or serious lateness | Major rework or client complaint | Hindered team flow

## How to Use
Step
1. Go to the 'KPI System' tab.
2. Input project, client, role, and scores for each team member.
3. Ensure the role matches exactly with the 'Role-Specific Weights' tab.
4. Scores must be 0–100. Use the 'Scoring Guide' tab if unsure.
5. 'Overall KPI %' and 'Color Code' are automatically calculated.
6. Use 'Individual' task type for solo tasks, 'Team' if it's shared.
7. Use this sheet monthly or per project to track performance.
8. You can filter, sort, or extend the sheet as needed.

## KPI Justification
RGA WOOD KPI SYSTEM – FINAL JUSTIFICATION & ROLL-OUT LOGIC
📌 Purpose
The RGA KPI System was designed to align performance tracking with real-world outputs, enabling your leadership team to make data-driven decisions around accountability, promotions, training, and operations. It’s not just a tracker—it’s your internal playbook for building a scalable, high-performance culture.
🔍 CORE JUSTIFICATIONS (Backed by Logic & Fixes)
1. ✅ Custom Role Weights (Fixed to 1.0)
Each role is scored using weights that reflect what actually matters in their job: Output, Timeliness, Accuracy, Teamwork, and Material Efficiency.
✅ Correction Made: Fabricator and CNC Operator weights now total 1.0, fixing prior inflation errors.
2. ✅ New Columns to Capture Reality
- Error/Revision Category – Track root causes of issues
- CSAT (Client Satisfaction Score) – Direct client feedback for PM accountability
- Planned vs. Actual Material Quantity – For cost-efficiency insights
- Material Efficiency % – Auto-calculated waste metric
Why It Matters: We're now measuring not just what was done, but how well and efficiently it was done—internally and externally.
3. ✅ Updated Scoring Guide
Defined performance bands for Material Efficiency let team leaders understand score meaning and give real feedback.
4. ✅ Updated 'How to Use' Guide
Step-by-step logic added to input CSAT, categorize revisions, and interpret scores to keep the team aligned.
🧠 Long-Term Use Case
- Identify consistent underperformance with cause
- Spot delays, errors, and cost overruns
- Link client feedback with internal performance
- Run performance reviews with hard data, not vibes
⚙️ Suggested Enhancements (Optional)
1. Dropdowns for Revision Category – For consistent tagging
2. Target % Columns – Compare actual vs. goal
3. Dashboard Tab – PivotCharts for trends, waste, CSAT, and error types

## KPI Details
Role | KPI Category | Description | Weight
Designer | Design Output | Number of completed design tasks (3D/Layout) | 40%
Designer | Timeliness | Submitted designs on or before due date | 20%
Designer | Accuracy | Designs passed QC with minimal revisions | 20%
Designer | Teamwork | Clear communication with PM, Estimator, and Production | 20%
Project Manager | Execution & Coordination | Ensures project milestones are met on time | 30%
Project Manager | Client Handling | Timely updates, professional handling of concerns | 20%
Project Manager | Documentation | Turnovers, contracts, reports are complete and on-time | 20%
Project Manager | Team Supervision | Guides team, resolves issues efficiently | 15%
Project Manager | Reporting & Feedback | Daily updates, communicates risks | 15%
Estimator | Cost Accuracy | Accurate BOM, reflects actual usage | 35%
Estimator | Speed of Output | Timely submission of estimates | 25%
Estimator | Coordination | Communicates changes with Designers and Inventory | 20%
Estimator | Teamwork | Supports Sales/PM with pricing discussions | 20%
Fabricator | Output Quantity | Number of units produced vs. target | 30%
Fabricator | Timeliness | Tasks completed within schedule | 25%
Fabricator | Accuracy | Proper cuts, alignment, drilling | 25%
Fabricator | Material Efficiency | Minimizes wastage of boards/hardware | 20%
CNC Operator | Cutting Accuracy | Precision and cleanliness of output | 35%
CNC Operator | Maintenance & Operation | Proper machine use, no downtime | 25%
CNC Operator | Timeliness | No bottleneck in CNC stage | 20%
CNC Operator | Material Efficiency | Optimized layouts reduce scrap | 20%
Painter | Finish Quality | Smooth, bubble-free finish, correct color | 35%
Painter | Prep & Dry Time | Proper sanding/putty, avoids delays | 25%
Painter | Clean Workspace | Maintains paint area and tools | 20%
Painter | Team Coordination | Clear turnover to next team (install/packaging) | 20%
Electrician | Wiring Accuracy | No rewiring needed, neat output | 35%
Electrician | Timeliness | Completed on-site or pre-wired as scheduled | 25%
Electrician | Tool Handling | Uses proper gear, no damage to tools | 20%
Electrician | Team Coordination | Collaborates with fabricators and painters | 20%
Project Coordinator / Admin | Inquiry Handling | Responds to leads within expected timeframe | 30%
Project Coordinator / Admin | Document Management | Updates CRM, files contracts, etc. | 30%
Project Coordinator / Admin | Scheduling Support | Aids in planning, calendar accuracy | 20%
Project Coordinator / Admin | Team Support | Supports PM/Accounting/Design as needed | 20%
Accounting | Collection Timeliness | Follows up, secures payments before due | 35%
Accounting | Billing Accuracy | Prepares correct SOAs and ORs | 30%
Accounting | Reporting | Provides cash flow & financial summaries | 20%
Accounting | Coordination | Works closely with PM/Admin during turnover | 15%